## Progress_Stages
Goal | Build a responsive dashboard for clients/advisors to monitor stocks, execute trades, and analyze portfolios in real time.
Stage & Objective | Tasks | Deliverables | Status
Analysis | Stakeholder Interviews: Gather needs from clients, advisors, and compliance teams. | Requirement Specification Document (SRS) | Functional and Non-functional Requirments are clear
Define requirements, scope, and feasibility. | Market Research: Evaluate APIs (Alpha Vantage, IEX Cloud) for real-time data. | API comparison matrix (cost, latency, features). | Researched and updated in Doc.
Use Case Definition:
Client: View stock market prices, Track portfolio performances, place orders, set alerts, Generate reports (FUN req)
Advisor: Bulk trades, client portfolio analysis, Generate reports, Annotate trades (e.g., "Tax-Loss Harvesting") (FUN req)
Regulatory Compliance: Identify FINRA/GDPR requirements for trade auditing. (N-FUN req)
Feasibility Study: Assess WebSocket scalability, Kafka for event streaming. (N-FUN req)
Planning | Tech Stack Finalization: | Project Plan (Gantt chart, sprint backlog).
Create timelines, allocate resources, and define risks. | Backend: Spring Boot (Microservices), Kafka, PostgreSQL Mongo DB, Netflix DGS, GraphQL API
Frontend: React.ts, Chart.js, AG-Grid. Tanstack Query, Bootstrap
Milestone Planning
Sprint 1: Auth + Market Data Service.
Sprint 2: Order Execution + Portfolio Tracking.
Sprint 3: Role-Based Views + Notifications.
Risk Management:
| Mitigate API rate limits (cache market data). | Risk Assessment Matrix.
Handle trade failures (dead-letter queues in Kafka).
Design | System Architecture: | Architecture Diagrams (C4, Deployment)
Architect the system and design UI/UX. | Microservices: Auth, Market Data, Order, Portfolio. | UI Mockups (Figma/Adobe XD).
| Event Flow: WebSocket → Kafka → Order Service → DB. | Swagger/OpenAPI Spec.
Database Design:
Tables: Users, Orders, Portfolios, Market_Data
UI Wireframes
Dashboard: Stock charts, order form, portfolio summary.
Role-Based Views: Advisor sees client lists + bulk actions.
API Contracts
REST: GET /portfolio, POST /orders
WebSocket: /topic/prices/{symbol}
Development | Backend: | Functional Microservices (Git repos).
Build and integrate components. | Set up Spring Boot microservices (Spring Cloud, Eureka).
Implement WebSocket (STOMP) for real-time prices.
Kafka producers/consumers for order events.
| Frontend | React Dashboard (Vercel/Netlify preview).
React.ts app with Redux (state management).
Chart.js for P&L trends, AG-Grid for holdings.
Integrations:
Mock Stock Market API (for testing).
Auth0/Keycloak for JWT-based roles.
Testing & Integration | Unit Tests: | Test Reports (JUnit, Postman).
Ensure reliability, performance, and security. | Spring Boot: MockMVC for APIs, Kafka test containers.
React: Jest + Testing Library.
Integration Tests:
Validate order flow: Frontend → Kafka → DB.
| Performance Tests: | Performance Metrics (Gatling reports).
Load test WebSocket (10K concurrent users).
Security Tests:
OWASP ZAP for vulnerabilities (e.g., SQLi, XSS).
Role-based access checks.
Maintaince | Alerts
Monitor, optimize, and scale. | Bug Fixes: Prioritize based on user feedback (e.g., trade failures). | Incident Reports (JIRA/ServiceNow).
Enhancements
| Add new chart types (e.g., candlestick). | Quarterly Release Plans.
Integrate real brokerage APIs (e.g., Alpaca).
Scaling
Kubernetes for microservices.
Redis cache for market data.
Compliance Updates:
Audit log retention policies.

## Analysis
Stock Market API Comparison (2025) | [5 empty] | Summery: | Key Decision Factors
Provider | Pricing (Free Tier) | Latency | Key Features | Limitations | Best For | Real-Time Needs: | Polygon.io (best latency) > IEX Cloud > Twelve Data.
Alpha Vantage | Free: 25 req/day | 500ms-1s | - Global equities, forex, crypto | Free tier very limited | Backtesting, research |  | Avoid Alpha Vantage for real-time (delayed by 5-15 mins in free tier).
| Paid: $49+/month |  | - Historical + real-time (delayed) | No true real-time |  | Global Coverage: | Twelve Data or Finnhub (supports forex/crypto).
|  |  | - Technical indicators (SMA, RSI) |  |  | Cost vs. Features: | Free Tier: IEX Cloud (50k msg/month) > Finnhub (60 req/min).
IEX Cloud | Free: 50k msg/month | 100-300ms | - Real-time US stocks (IEX exchange) | Limited global coverage | US-focused trading apps |  | Paid Tier: Polygon.io for HFT, Twelve Data for affordability.
| Paid: 9−9−999/month |  | - Fundamental data (EPS, dividends) | No forex/crypto |  | Advanced Features: | Polygon.io: Tick-level order book data.
|  |  | - WebSocket support |  |  |  | Finnhub: News sentiment + fundamentals.
Polygon.io | Free: None | <100ms (WebSocket) | - Ultra-low latency US stocks/options | Expensive for small projects | High-frequency trading (HFT)
| Paid: 29−29−999/month |  | - Real-time + historical tick data | Complex API |  | KEY TAKES | For Local Development: Use IEX Cloud (free WebSocket + low latency).
|  |  | - Institutional-grade |  |  |  | For Production: Switch to Polygon.io if scaling to high-frequency trades.
Twelve Data | Free: 8 req/day | 300-700ms | - Global stocks, forex, crypto | Free tier restrictive | Multi-asset dashboards |  | For Global Markets: Twelve Data or Finnhub.
| Paid: 8−8−99/month |  | - Real-time + WebSocket | Fewer indicators
- Simple REST API
Finnhub | Free: 60 req/minute | 200-500ms | - Global equities, forex, crypto | No WebSocket in free tier | AI-driven stock analysis
| Paid: 50−50−500/month |  | - News sentiment analysis | Rate limits
- Earnings calendar

## Planning
## Realtime-invest-bank-trading-and-dashboard tools and technologies
Objective | Tools | Service/component name | Accessing URL | port | userId | password | Technologies
Database | Postgres
NoSQL | MongoDB
Security | keycloak
Monitoring | Promotheus
Dashboard | Graphana
Tracing | Zipkin
CI/CD | github actions
CI/CD | Docker image repo
Messeging | Kafka
Messeging | Zookeper
CodeQuality | SonarQube
Secrets | Vault
Performance | K6-Performance
Architecture/ Design patterns | ## Spring Cloud services
Microservices architecture GATEWAY pattern | Api gateway | spc-api-gateway | http://localhost:8060 | 8060 |  |  | Authentication, monitoring Resiliency, Rate limiting, Loadbancer Routing
| Service registry | spc-service-registry | http://localhost:8761 | 8761 |  |  | Netflix, Eureka
| Config Server | spc-config-server | http://localhost:8088 | 8088 |  |  | Config management from Git, hashcorp
## JPM WM services
| Keycloak | kc-auth-service
| Spring boot | jpm-advisory-service | http://localhost:8082 | 8082 |  |  | Netflix DGS, GraphQL API Spring Boot, lombok
jpm-wealth-mgmt-service
jpm-retirement-service
jpm-report-service
jpm-notification-service
jpm-investment-service
jpm-education-service
|  | jpm-client-service | http://localhost:8081 | 8081 |  |  |  | Mapstruct, spring boot, lombok
| React TS | jpm-wm-frontend | http://localhost:3000 |  |  |  | React, Typescript, Tanstack Query, ag-grid,Bootstrap
AI- Era | ## AI services
| Spring AI | jpm-ai-service |  |  |  |  | Ollama, Deepseek Spring AI
[5 empty] | Requirement | Monolithic Approach | My Microservice Solution
[5 empty] | Scaling | Vertical only | Auto-scaling per service
[5 empty] | Deployments | High-risk | Isolated service updates
[5 empty] | Tech Diversity | Limited | Polyglot (Spring/React/Mapstruct/GraphQL/NetflixDGS)
[5 empty] | Speed to Market | Fastest | Slower init
[5 empty] | Complexity | Low | Very High

## Maintaince
Maintaince

## StatusCodes
HTTP status directory
BAD_REQUEST | This indicates a problem with the request. Retrying the same request is not likely to succeed. An example would be a query or argument that cannot be deserialized. | 400 Bad Request
FAILED_PRECONDITION | The operation was rejected because the system is not in a state required for the operation’s execution. For example, the directory to be deleted is non-empty, an rmdir operation is applied to a non-directory, etc. Use UNAVAILABLE instead if the client can retry just the failing call without waiting for the system state to be explicitly fixed. | 400 Bad Request, or 500 Internal Server Error
INTERNAL | This indicates that an unexpected internal error was encountered: some invariants expected by the underlying system have been broken. This error code is reserved for serious errors. | 500 Internal Server Error
NOT_FOUND | This could apply to a resource that has never existed (e.g. bad resource id), or a resource that no longer exists (e.g. cache expired). Note to server developers: if a request is denied for an entire class of users, such as gradual feature rollout or undocumented allowlist, NOT_FOUND may be used. If a request is denied for some users within a class of users, such as user-based access control, PERMISSION_DENIED must be used. | 404 Not Found
PERMISSION_DENIED | This indicates that the requester does not have permission to execute the specified operation. PERMISSION_DENIED must not be used for rejections caused by exhausting some resource or quota. PERMISSION_DENIED must not be used if the caller cannot be identified (use UNAUTHENTICATED instead for those errors). This error does not imply that the request is valid or the requested entity exists or satisfies other pre-conditions. | 403 Forbidden
UNAUTHENTICATED | This indicates that the request does not have valid authentication credentials but the route requires authentication. | 401 Unauthorized
UNAVAILABLE | This indicates that the service is currently unavailable. This is most likely a transient condition, which can be corrected by retrying with a backoff. | 503 Unavailable
UNKNOWN